## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | 4
PROJECT NAME | Learning Management System
PROJECT MENTOR (sponsor) | Bibhu Prasad Sahoo
TEAM MEMBERS | Arshiya Noureen
Kushal Mangla
Sanyam Agrawal
Shreyas Deb
Vishak Kashyap K

## Status
PROJECT NUMBER | 4
PROJECT NAME | Learning Management System With Personalised Recommandations
PROJECT MENTOR | Bibhu Prasad Sahooo
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
Week 1 (January 13 - January 19)
Client Meeting 1 - 16th Jan | Coordination | Vishak | 0.5 | 0.5 | Done | Includes MoMs | 0 | 0
GIT Repository Setup | Preparation | Shreyas | 0.5 | 0.3 | Done |  | 0.2 | 66.6667
Client Meeting 2 - 18th Jan | Coordination | Kushal | 1 | 1 | Done | Includes MoMs | 0 | 0
Learn React | Preparation | Sanyam | 4 | 3 | Done |  | 1 | 33.3333
Researching and Installing Moodle System | Preparation | Shreyas | 2 | 1.5 | Done |  | 0.5 | 33.3333
Project Synopsis Writeup | Documentation | Arshiya | 2 | 2 | Done |  | 0 | 0
Team Meeting - 19th Jan | Coordination | Kushal | 1 | 0.5 | Done | Discussed our strengths with regards to tech stacks | 0.5 | 100
Status tracker | Documentation | Sanyam | 1 | 1 | Done |  | 0 | 0
Week 2 (January 20 - January 26)
Client Meeting 3 - 25th Jan | Coordination | Shreyas, Kushal | 0.25 | 0.2 | Done | Includes MoMs | 0.05 | 25
Team Meeting - 25th Jan | Coordination | Arshiya, Sanyam | 0.5 | 0.4 | Done | Discussed the roles and responsibility division | 0.1 | 25
Status tracker | Documentation | Vishak | 1 | 0.75 | Done |  | 0.25 | 33.3333
Identify Role Owners | Preparation | Shreyas, Sanyam, Arshiya, Kushal, Vishak | 0.75 | 0.75 | Done |  | 0 | 0
Week 3 (January 27 – February 02)
Project Plan Writeup | Documentation | Shreyas, Vishak | 1.5 | 1 | Done | Discussed the approach to our project | 0.5 | 50
Status tracker | Documentation | Vishak | 0.5 | 0.5 | Done |  | 0 | 0
Figma Design for the Project | Design | Vishak, Kushal | 2 | 2 | Done | UI/UX Wireframe design for the project | 0 | 0
Set Up Backend, Moodle on Local System | Preparation | Shreyas, Sanyam, Arshiya | 3.25 | 3 | Done |  | 0.25 | 8.3333
Week 4 (February 03 - February 09)
Client Meeting | Coordination | Shreyas | 1 | 0.75 | Done | Includes MoMs
Project Specification report for the client | Documentation | Kushal, Sanyam | 1 | 1 | Done |  | 0 | 0
Moodle API Documentation | Documentation | Arshiya | 1 | 1 | Done |  | 0 | 0
Basic Auth and Login API | Development | Shreyas | 2 |  | Done
Updated Figma Design upon client feedback | Design | Vishak | 2 | 2 | Done |  | 0 | 0
Installing moodle on VM | Preparation | Sanyam | 1 | 1 | Done |  | 0 | 0
Exploring Auto Login to moodle with single click or link | Preparation | Arshiya | 1 |  | Ongoing
Status Tracker | Documentation | Vishak | 0.5 | 0.5 | Done |  | 0 | 0
Week 5 (February 10 – February 16)
Develop content upload feature for Admins, Coaches | Development | Kushal, Vishak | 2 |  | Ongoing
Final Figma Design | Design | Vishak | 1 | 2 | Done |  | -1 | 50
Implement User Role Management | Development | Shreyas, Sanyam, Arshiya | 3 |  | Ongoing
Deploying Moodle on VM and Web Services | Development | Sanyam | 3 | 3 | Done
Work on Moodle Integration | Development | Sanyam, Shreyas | 3 | 4 | Done |  | -1 | 25
Client Meeting - 11th Feb, 2025 | Coordination | Arshiya | 1 | 1 | Done | Includes MoMs | 0 | 0
Status Tracker | Documentation | Vishak | 0.5 | 0.5 | Done |  | 0 | 0
SRS Document | Documentation | Arshiya, Kushal, Shreyas | 2 | 2.5 | Done
Login Page, Sign Up Page, Landing Page Frontend |  | Kushal, Vishak | 3 | 2.5 | Done |  | 0.5 | 20
Week 6 (February 17 – February 23)
Implement User Role Management | Development | Shreyas, Sanyam, Arshiya | 2 | 2 | Done |  | 0 | 0
Develop content upload feature for Admins, Coaches | Development | Kushal, Vishak | 2 | 2 | Ongoing |  | 0 | 0
Implement Learner Dashboard – Frontend | Development | Kushal, Vishak | 1.5 | 1.5 | Done |  | 0 | 0
Implement Analytics Page – Frontend | Development | Kushal | 1 | 1 | Done |  | 0 | 0
Implement Coach Dashboard – Frontend | Development | Vishak | 1 | 1 | Done |  | 0 | 0
Status Tracker | Documentation | Arshiya | 0.5 | 0.5 | Done |  | 0 | 0
Client Meeting | Coordination | Vishak,Shreyas,Kushal | 1 | 1 | Done | Includes MoMs | 0 | 0
Week 7 (February 24 – March 02)
Implement User Role Management | Development | Shreyas,Sanyam,Arshiya | 2 | 2 | Done |  | 0 | 0
Connect Frontend with Backend | Development | Shreyas,Kushal,Sanyam | 2 | 2 | Done |  | 0 | 0
Implement Learner Dashboard – Frontend | Development | Kushal,Vishak | 1.5 | 1 | Done |  | 0.5 | 33.33
Implement Coach Dashboard – Frontend | Development | Kushal,Vishak | 1 | 1 | Done |  | 0 | 0
Define All learner routes in backend | Development | Shreyas | 2 | 2 | Done |  | 0 | 0
Status Tracker | Documentation | Sanyam | 0.5 | 0.5 | Done |  | 0 | 0
Note: Client Meet was not held this week on account of Midsems
Week 8 (March 03 – March 09)
Implement User Role Management | Development | Shreyas,Sanyam,Arshiya | 3 | 4 | Done |  | 0 | 0
Implement Learner Dashboard – Frontend | Development | Kushal,Vishak | 1.5 | 2 | Done |  | 0.5 | 33.33
Implement Coach Dashboard – Frontend | Development | Kushal,Vishak | 1 | 1 | Done |  | 0 | 0
Implement-Courses Page – Frontend | Development | Kushal,Vishak | 2 | 2.5 | Done |  | 0.5 | 25
Implement Backend logic for Courses | Development | Shreyas,Sanyam | 3 | 4 | Done |  | 1 | 33.33
Adding Courses using Moddle Web Services | Development | Sanyam | 2 | 2 | Done |  | 0 | 0
Client Meeting | Coordination | Vishak,Sanyam,Kushal | 1 | 1 | Done | Includes MoMs | 0 | 0
Status Tracker | Documentation | Shreyas | 0.5 | 0.5 | Done |  | 0 | 0
Week 9 (March 11 – March 16)
Learning about Recommendation Systems | Development | Shreyas | 5 | 4 | Done |  | 1 | 25
Backend Integration with Frontend and Moodle | Development | Kushal | 4 | 5 | Done
Implement Learner Dashboard – Frontend | Development | Kushal,Vishak | 3 | 3 | Done
Implement Coach Dashboard – Frontend | Development | Shreyas | 3 |  | Done
Implement-Courses Page – Frontend | Development | Kushal,Vishak | 3 | 2 | Done
Team Meet | Coordination | Arshiya | 1 | 1 | Done |  | 0 | 0
Backend Routes for learner and coaches | Development | Sanyam | 6 | 5 | Done |  | 1 | 20
Status tracker | Development | Sanyam, Kushal | 1 | 0.5 | Done
Week 10 (March 17 – March 23)
Implement Coach Dashboard – Frontend | Development | Shreyas | 2 | 2 | Done |  | 0 | 0
Implement Learner Analysis – Frontend | Development | Arshiya | 4 | 4 | Done |  | 0 | 0
Search and filter for courses | Development | Kushal, Vishak | 3 | 4 | Done |  | -1 | 25
Handling course content Routes | Development | Kushal | 4 | 3 | Done |  | 1 | 33.3333
Displaying video inline and adding controls | Development | Kushal | 3 | 4 | Done |  | -1 | 25
Making code modular | Development | Shreyas | 2 | 2.5 | Done |  | -0.5 | 20
Track Learner Progress | Development | Kushal, Shreyas, Vishak | 5 | 5 | Done |  | 0 | 0
Backend Routes for learner Progress | Development | Sanyam | 3 | 2 | Done |  | 1 | 50
R1 Video | Documentation | Shreyas, Sanyam | 4 | 4 | Done |  | 0 | 0
R1 Presentation | Documentation | Vishak | 3 | 2.5 | Done |  | 0.5 | 20
Status Tracker | Documentation | Kushal, Sanyam | 1 | 0.5 | Done |  | 0.5 | 100
Week 11 (March 24 – March 30)
Change of Frontend based on R1 Feedback | Development | Kushal, Vishak | 5 | 4 | Done |  | 1 | 25
Work on Recommendaton Engine | Development | Shreyas | 5 | 6.5 | Done |  | -1.5 | 23.0769
Client Meeting Setup | Coordination | Arshiya | 0.5 |  | Delayed
Coach Role Management | Development | Sanyam | 2 |  | Done
Test Plan Tracker | Documentation | Vishak,Arshiya | 1 | 1 | Done |  | 0 | 0
Status Tracker | Documentation | Sanyam | 0.5 | 0.5 | Done |  | 0 | 0
Week 12 (March 31 – April 06)
Recommendation Engine Data Collection | Development | Shreyas | 5 | 4 | Done |  | 1 | 25
Frontend Revamp | Development | Kushal, Vishak | 5 |  | Done
Backend Refractor | Development | Sanyam | 5 | 4 | Done |  | 1 | 25
Test Plan Tracker | Testing | Vishak, Arshiya | 1 | 1 | Done |  | 0 | 0
Client Meeting | Coordination | Arshiya | 1 | 1 | Done |  | 0 | 0
R1 Evaluations | Coordination | Sanyam,Kushal,Vishak,Shreyas,Arshriya | 1 | 1 | Done |  | 0 | 0
Status Tracker | Documentation | Sanyam | 0.5 | 1 | Done |  | -0.5 | 50
Week 13 (April 07 – April 13)
Recommendation Engine Data Collection | Development | Shreyas | 5 | 4 | Done |  | 1 | 25
Frontend Revamp | Development | Kushal, Vishak | 5 |  | Done
Test Plan Tracker | Testing | Vishak, Arshiya | 1 | 1 | Done |  | 0 | 0
Client Meeting | Coordination | Arshiya | 1 |  | Delayed
Team Meeting | Coordination | Sanyam | 1 | 1 | Done |  | 0 | 0
Status Tracker | Documentation | Sanyam | 0.5 | 1 | Done |  | -0.5 | 50
Week 14 (April 14 – April 21)
Recommendation Engine Coding | Development | Shreyas | 3 | 3 | Done |  | 0 | 0
Recommendation Engine Integration | Development | Shreyas, Vishak | 2 | 2.5 | Done |  | -0.5 | 20
Frontend Bugs Fix | Development | Kushal,Shreyas | 3 | 3.5 | Done |  | -0.5 | 14.2857
Progress tracking(Frontend + Backend | Development | Sanyam | 3 | 3 | Done |  | 0 | 0
Plugin For Fetching Tags from Moodle | Development | Sanyam | 3 | 3 | Done |  | 0 | 0
Enabling Moodle SSO | Development | Sanyam | 3 | 3 | Done |  | 0 | 0
Integration Testing | Testing | Vishak | 1 | 1 | Done |  | 0 | 0
Final Changes to Documentation | Documentation | Vishak,Kushal,Arshiya | 1 | 1 | Done |  | 0 | 0
Final Client Meet | Coordination | Shreyas,Kushal,Vishak | 1 | 1 | Done |  | 0 | 0
Status tracker | Documentation | Sanyam | 0.5 | 0.5 | Done |  | 0 | 0